## ToDo
ToDo List
ID | Story | Estimation | Priority | Status | Sprint | Key
10 | As a User, I would like to have positive visuals when I guess correctly to keep me entertained. | 8 | MED | IP |  | Story Priority: HI (high), MED (medium), LOW (low)
16 | As a User, I would like to be able to see my rank on the leaderboard to motivate me. | 33 | LOW | W |  | Story Status: W (waiting), IP (in progress), T (testing), D (done)
1 | As a User, I would like the ability to access different levels to have a sense of progresson. | 5 | HI | IP
6 | As a User, I would like to share my score on social media to show my friends. | 13 | LOW | W
14 | As a User, I would like the ability to see triva about the country so I can learn more about it. | 8 | MED | W
9 | As a User, I would like to have a map show the locaiton of correct country to improve my geography skills. | 5 | MED | W
13 | As a User, I would like to have a limit on the number of guesses so that the game is a challenge. | 1 | MED | IP
5 | As a User, I would like to be able to see hints so that I do not get stuck. | 2 | MED | IP
3 | As a User, I would like the game to increase in difficulty over time in order to provide a challenge. | 5 | MED | W
15 | As a user, I would like the have multiple game types in order to keep me engaged over time. | 13 | MED | W
8 | As a User, I would like to be able to adjust the settings to customize the game. | 3 | Null | Done | 5
2 | As a User, I would like the ability to save my progress so that I can return to where I left off. | 3 | Null | Done | 4
4 | As a User, I would like to sort levels by contient/region to customize gameplay. | 8 | Null | Done | 5
11 | As a User, I want to play a version of the gamemode with spelling in order to learn to spell. | 13 | Null | Done | 5
12 | As a User, I would like the flag to gradually be revealed so I can recieve different amounts of points. | 13 | Null | Done | 4
7 | As a User, I would like the ability to check my current score to see my progress. | 5 | Null | Done | 4
18 | As a User, I would like the ability to start the game from the main menu in order to begin playing for points. | 2 | Null | Done | 1
19 | As a User, I would like the ability to adjust the sound settings in order to set it to my prefrences. | 5 | Null | Done | 2
17 | As a User, I would like the game to display flags in a quiz format to learn flag names. | 8 | Null | Done | 3
21 | As a User, I would like a gamemode where I guess flags through multiple choice to initally learn the names of flags. | 13 | Null | Done | 3
20 | As a User, I would like for the ability to go to a gamemode where the names of flags are asked in a random order within a certain amount of time in order to challenge myself. | 5 | Null | Done | 2
21 | As a User, I would like to be able to access a menu of options in order to navigate through the game. | 5 | Null | Done | 1
23 | As a User, I would like to be shown flags from around the world in order to answer questions about them. | 13 | Null | Done | 2
22 | As a User, I would like the main menu to be visually appealing in order to hook me into the game. | 13 | Null | Done | 3