## Sprint 1
Sprint 1 Backlog | Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal: Make basic menu structure and gamemode management.
User Story | Type | Tasks | Story Points | Story Points Completed | Team Member Name | Percent Contributed to Story
As a User, I would like to be able to access a menu of options in order to navigate through the game. | F,(T) | Create basic splash screen | 5 | 5 | Cody Otterbine | 15%
|  | Create main menu screen |  |  | Akira Uchiyamada | 30%
|  | Create menu options for starting the game |  |  | Ruben Perez | 10%
|  | Create menu options for choosing the gamemode |  |  | Eddie Garcia | 20%
[5 empty] | Asah Oghenerukevwe | 15%
[5 empty] | Kazi Abdul Muktadir | 10%
As a User, I would like the ability to start the game from the main menu in order to begin playing for points. | F,(T) | Create system to start game scene | 13 | 13 | Cody Otterbine | 15%
|  | Create system to implement gamemode settings |  |  | Akira Uchiyamada | 20%
[5 empty] | Ruben Perez | 15%
[5 empty] | Eddie Garcia | 15%
[5 empty] | Asah Oghenerukevwe | 15%
[5 empty] | Kazi Abdul Muktadir | 20%
|  | Total: | 26 | 26

## Sprint 2
Sprint 2 Backlog | Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal: To add basic game scenes and create a flag database.
User Story | Type | Tasks | Story Points | Story Points Completed | Team Member Name | Percent Contributed to Story
As a User, I would like the ability to adjust the sound settings to set the values to my personal prefrences. | F,(T) | Add settings menu option. | 5 | 5 | Cody Otterbine | 20%
|  | Add radio button to turn on/off music. |  |  | Akira Uchiyamada | 30%
|  | Add slider for volume level. |  |  | Ruben Perez | 0%
|  | Add radio button to turn on/off sound effects. |  |  | Eddie Garcia | 30%
|  | Add music for when in-game. |  |  | Asah Oghenerukevwe | 20%
[5 empty] | Kazi Abdul Muktadir | 0%
As a User, I would like for the ability to go to a gamemode where the names of flags are asked in a random order within a certain amount of time in order to challenge myself. | F,(T) | Add gamemode to game selection menu. | 13 | 13 | Cody Otterbine | 15%
|  | Create random flag picker system. |  |  | Akira Uchiyamada | 30%
|  | Create countdown timer. |  |  | Ruben Perez | 15%
|  | Create points system based off timer. |  |  | Eddie Garcia | 0%
|  | Add basic flag display system. |  |  | Asah Oghenerukevwe | 10%
|  | Add system to check which flags have already been guessed. |  |  | Kazi Abdul Muktadir | 30%
As a User, I would like to be shown flags from around the world in order to answer questions about them. | NF,(KA) | Create database to contain different flags. | 8 | 8 | Cody Otterbine | 20%
|  | Create/acquire high quality images of flags. |  |  | Akira Uchiyamada | 15%
|  | Create sub-groups of flags for certain regions. |  |  | Ruben Perez | 20%
|  | Attach flag database to quiz system to use in questions. |  |  | Eddie Garcia | 15%
[5 empty] | Asah Oghenerukevwe | 10%
[5 empty] | Kazi Abdul Muktadir | 20%
|  | Total: | 26 | 26

## Sprint 3
Sprint 3 Backlog | Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal: Create quiz game framework.
User Story | Type | Tasks | Story Points | Story Points Completed | Team Member Name | Percent Contributed to Story
As a User, I would like a gamemode where I guess flags through multiple choice to initally learn the names of flags. | F,(T) | Add gamemode to game selection menu. | 8 | 8 | Cody Otterbine | 15%
|  | Create multiple-choice interface. |  |  | Akira Uchiyamada | 25%
|  | Create answer-generation system. |  |  | Ruben Perez | 20%
|  | Add graphic design elements. |  |  | Eddie Garcia | 20%
[5 empty] | Asah Oghenerukevwe | 0%
[5 empty] | Kazi Abdul Muktadir | 20%
As a User, I would like the game to display flags in a quiz format to learn flag names. | F,(KA) | Add quiz interface system. | 8 | 8 | Cody Otterbine | 10%
|  | Add system to adjust answering format based on gamemode selected. |  |  | Akira Uchiyamada | 30%
|  | Add points counter. |  |  | Ruben Perez | 15%
|  | Add system to adjust fail condition based on the selected gamemode. |  |  | Eddie Garcia | 0%
[5 empty] | Asah Oghenerukevwe | 25%
[5 empty] | Kazi Abdul Muktadir | 20%
As a User, I would like the main menu to be visually appealing in order to hook me into the game. | NF,(KA) | Change background to gradient. | 8 | 8 | Cody Otterbine | 45%
|  | Align menu symetirically. |  |  | Akira Uchiyamada | 0%
|  | Create splash screen art. |  |  | Ruben Perez | 20%
|  | Create graphic design elements for menu options. |  |  | Eddie Garcia | 20%
|  | Create main menu background art. |  |  | Asah Oghenerukevwe | 10%
[5 empty] | Kazi Abdul Muktadir | 10%
|  | Total: | 26 | 26

## Sprint 4
Sprint 4 Backlog | Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal: Make game playable enough for User Testing.
User Story | Type | Tasks | Story Points | Story Points Completed | Team Member Name | Percent Contributed to Story
As a User, I would like the ability to save my progress so that I can return to where I left off. | F,(T) | Create system that creates save files | 8 | 8 | Cody Otterbine | 0%
|  | Add interface for managing saves or hook files to accounts |  |  | Akira Uchiyamada | 10%
|  | Add more data to save file (fails, games played, etc.) |  |  | Ruben Perez | 20%
[5 empty] | Eddie Garcia | 15%
[5 empty] | Asah Oghenerukevwe | 30%
[5 empty] | Kazi Abdul Muktadir | 25%
As a User, I would like the flag to gradually be revealed so I can recieve different amounts of points. | F,(KA) | Add time counter for gradual flag reveal | 8 | 8 | Cody Otterbine | 35%
|  | Create system that gradually adds pixels to image over time |  |  | Akira Uchiyamada | 30%
|  | Hook up flag database to flag reveal system. |  |  | Ruben Perez | 15%
|  | Create time-based scoring system |  |  | Eddie Garcia | 20%
[5 empty] | Asah Oghenerukevwe | 0%
[5 empty] | Kazi Abdul Muktadir | 0%
As a User, I would like the ability to check my current score to see my progress. | F,(T) | Add visual score counter | 8 | 8 | Cody Otterbine | 15%
|  | Make score perpetuate across multiple scenes |  |  | Akira Uchiyamada | 10%
|  | Include Time counter and typing errors in composite score |  |  | Ruben Perez | 15%
|  | Send score data to save file system and highscore board system |  |  | Eddie Garcia | 15%
[5 empty] | Asah Oghenerukevwe | 25%
[5 empty] | Kazi Abdul Muktadir | 20%
|  | Total: | 26 | 26

## Sprint 5
Sprint 5 Backlog | Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal: Make game more varied and engaging by including additional features.
User Story | Type | Tasks | Story Points | Story Points Completed | Team Member Name | Percent Contributed to Story
As a User, I would like to be able to adjust the settings to customize the game. | F,(T) | Add settings option to main menu. | 8 | 8 | Cody Otterbine | 15%
|  | Merge old sound adjustment into settings menu |  |  | Akira Uchiyamada | 30%
|  | Add country of orgin prefrences into menu |  |  | Ruben Perez | 5%
|  | Add languages to prefrences menu |  |  | Eddie Garcia | 20%
[5 empty] | Asah Oghenerukevwe | 20%
[5 empty] | Kazi Abdul Muktadir | 10%
As a User, I would like to sort levels by contient/region to customize gameplay. | NF,(KA) | Organize flag database with additonal catagories | 8 | 8 | Cody Otterbine | 20%
|  | Create new gamemode type that includes certain catagories |  |  | Akira Uchiyamada | 15%
|  | Add option to select contient/region of flags included in game |  |  | Ruben Perez | 20%
|  | Add additional regional-specific flags to database as needed. |  |  | Eddie Garcia | 15%
[5 empty] | Asah Oghenerukevwe | 10%
[5 empty] | Kazi Abdul Muktadir | 20%
As a User, I want to play a version of the gamemode with spelling in order to learn to spell country names. | F,(T) | Replace multiple choice system for country guessing | 8 | 8 | Cody Otterbine | 20%
|  | Create new system that uses hangman style input |  |  | Akira Uchiyamada | 30%
|  | Create system to randomly generate country names with blanks |  |  | Ruben Perez | 20%
|  | Create system to monitor keyboard inputs and track errors |  |  | Eddie Garcia | 0%
[5 empty] | Asah Oghenerukevwe | 10%
[5 empty] | Kazi Abdul Muktadir | 20%
|  | Total: | 26 | 26