## Cody (Sprint 1)
Team Member Name: | Cody Otterbine
Roles Played This Week: | Product Owner, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Acted as Product Owner during Spring Review, Created and Ran Focus Group, Helped Design Menu Layout,
Role duties and work to be performed next week | Act as Scrum Master, Help Develop Reveal Function for Game, Conduct Sprint Reviews, Conduct Daily Scrum Meetings
Issues Enountered | None
Issued Resolved | None

## Cody (Sprint 2)
Team Member Name: | Cody Otterbine
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Added countdown timer for random-order-time trial gamemode, created random flag picker system, helped fill flag database, acquired high quality flag images, created product backlog, created sprint backlog
Role duties and work to be performed next week | Help Develop Reveal Function for Game, add graphic design elements, improve overall visual apperence to game
Issues Enountered | None
Issued Resolved | None

## Cody (Sprint 3)
Team Member Name: | Cody Otterbine
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Added new background elements to menu, created splash screen art, created background menu art, created Team member report, updated Product backlog and sprint backlog
Role duties and work to be performed next week | Act as Scrum Master, Conduct Sprint Reviews, Conduct Daily Scrum Meetings, add hints system, acquire images for use in triva
Issues Enountered | None
Issued Resolved | None

## Cody (Sprint 4)
Team Member Name: | Cody Otterbine
Roles Played This Week: | Scrum Master, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Ran sprint meetings and checked on other scrum members, helped update and write Configuration Management Plan, Implemented gradual flag reveal system, helped implement score
Role duties and work to be performed next week | Act as Product Owner, organize flag database with new catagories, update Team Member Report and Product Backlog
Issues Enountered | None
Issued Resolved | None

## Cody (Sprint 5)
Team Member Name: | Cody Otterbine
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Updated and managed product backlog, sprint backlog, and team member reports, helped add new flags and reorganize database, ran usability study
Role duties and work to be performed next week | Add new visual updates to game graphics, create game logo, assit in updated configuration management plan
Issues Enountered | None
Issued Resolved | None

## Akira (Sprint 1)
Team Member Name: | Akira Uchiyamada
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Wrote Platform Document, Wrote Intial Code, Created intial menu for game, added in highscores function into game, created github
Role duties and work to be performed next week | Act as Product Owner, conduct focus group, help particpate in sprint reviews
Issues Enountered | None
Issued Resolved | None

## Akira (Sprint 2)
Team Member Name: | Akira Uchiyamada
Roles Played This Week: | Product Owner, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Acted as Product Owner during Sprint Review, added settings menu, added radio button options for music, added flag display system, added gamemode selection menu, created points system
Role duties and work to be performed next week | Act as Scrum master, add flag multiple choice system, help particpate in sprint reviews
Issues Enountered | None
Issued Resolved | None

## Akira (Sprint 3)
Team Member Name: | Akira Uchiyamada
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Updated SRS, updated platform document, added quiz interface system, added points counter, added system for fail condition based on selected gamemode
Role duties and work to be performed next week | Add flag reveal system, update Use case models, update platform document
Issues Enountered | None
Issued Resolved | None

## Akira (Sprint 4)
Team Member Name: | Akira Uchiyamada
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created flag reveal game mechanic, helped implement visual score counter, updated Use Case Models, Updated SRS
Role duties and work to be performed next week | Act as scrum master, help create test plan documents, help update GRL and UCM Models
Issues Enountered | None
Issued Resolved | None

## Akira (Sprint 5)
Team Member Name: | Akira Uchiyamada
Roles Played This Week: | Scrum Master, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Ran sprint meetings and checked on other scrum members, helped create Test plan documentation, created hang-man style guessing gamemode implementation
Role duties and work to be performed next week | Create new gamemodes, update platform document, act as Scrum member again, create leaderboard system
Issues Enountered | None
Issued Resolved | None

## Ruben (Sprint 1)
Team Member Name: | Ruben Perez
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Designed Inital App Mockups, Commited some intial programming changes to app, created and set up Kanban Board, helped create use case models
Role duties and work to be performed next week | Add new features into app, fully flesh out high-score function in game, re-design interface to be more in line with focus group, help with focus group
Issues Enountered | None
Issued Resolved | None

## Ruben (Sprint 2) 1
Team Member Name: | Ruben Perez
Roles Played This Week: | Scrum Master
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Ran sprint meetings and checked on other scrum members, started configuration plan, helped add features to random-order-countdown gamemdoe, helped acquire flags for database.
Role duties and work to be performed next week | Add new features into app, fully flesh out high-score function in game, re-design interface to be more in line with focus group, help with focus group
Issues Enountered | None
Issued Resolved | None

## Ruben (Sprint 3)
Team Member Name: | Ruben Perez
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Updated Kanban board, updated configuration plan, helped to create new gamemode system, helped to add interface for sound settings.
Role duties and work to be performed next week | Updated Kanban, help create graphic design elements for main menu, help create Quiz interface system
Issues Enountered | None
Issued Resolved | None

## Ruben (Sprint 4)
Team Member Name: | Ruben Perez
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Helped create system for managing save data, updated Kanban board, helped create architecture and design patterns documents
Role duties and work to be performed next week | Act as Product Owner, updated configruation management plan, help reorganize flag database with additional catagories
Issues Enountered | None
Issued Resolved | None

## Ruben (Sprint 5)
Team Member Name: | Ruben Perez
Roles Played This Week: | Product Owner, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Acted as Product Owner during Sprint Review, updated configuration managemenrt plan/SRS, reorganized flag database with new catagories, helped create hangman-style input
Role duties and work to be performed next week | Update Kanban/Platform documents, create new visual assets for game, add more flags from non-countries to database
Issues Enountered | None
Issued Resolved | None

## Eddie (Sprint 1)
Team Member Name: | Eddie Garcia
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Helped to add input on intial app mockup, created the software requierments specification document, and use case models document, helped with focus group, adding contributions to Github
Role duties and work to be performed next week | Find and create flag assets for use in game, craft the tiers system for in-game progression, particpate in Daily Scrum meetings, help with focus group
Issues Enountered | None
Issued Resolved | None

## Eddie (Sprint 2)
Team Member Name: | Eddie Garcia
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created GRL and Use Case Map models, assisted in commits in order to add music and music settings to game, organized flags into subgroups and formatted database accoridingly
Role duties and work to be performed next week | Act as Product Owner, help run Sprint Review, update GRL and UCM, help add multiple-choice functionality
Issues Enountered | None
Issued Resolved | None

## Eddie (Sprint 3)
Team Member Name: | Eddie Garcia
Roles Played This Week: | Product Owner, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Acted as Product owner during sprint review, updated GRL and use case maps, helped create assets to make game more visually appealing, added commits to github
Role duties and work to be performed next week | Act as Scrum Master, help add reveal game mechanic, assit in creation of trivia questions, add additonal flags and their data to database
Issues Enountered | None
Issued Resolved | None

## Eddie (Sprint 4)
Team Member Name: | Eddie Garcia
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Helpd to add reveal game mechanic, helped create save game system, updated Sprint Backlog and Product Backlog Accordingly
Role duties and work to be performed next week | Update GRL and UCM Models Documents, help perform usability study, help create hangman style input
Issues Enountered | None
Issued Resolved | None

## Eddie (Sprint 5)
Team Member Name: | Eddie Garcia
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Updated GRL and UCM Models Documents, helped perform usability study, helped add new flags and catagories to database, helped create expanded settings menu
Role duties and work to be performed next week | Act as Scrum Master, help create test plan documents, update configruation management plan, update GRL and UCM
Issues Enountered | None
Issued Resolved | None

## Asah (Sprint 1)
Team Member Name: | Asah Oghenerukevwe
Roles Played This Week: | Scrum Master
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created the product backlog and sprint backlogs, helped to initiate the focus group, contributed to app gamemode design, ran daily Scrum meetings, lead Sprint Review, determined what would be on backlog
Role duties and work to be performed next week | Act as Owner and understand from that perspective, help design flag and other game assets, test game for fun and functionality, manage Kanban board.
Issues Enountered | None
Issued Resolved | None

## Asah (Sprint 2)
Team Member Name: | Asah Oghenerukevwe
Roles Played This Week: | Developer, Scrum Member
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created domain model and detailed design document, helped attach the database to the app, created points system based off of timer for the random-time-attack gamemode
Role duties and work to be performed next week | Update and finish domain model and detailed design document, help create visual assets to make game more appealing, help create quiz format system
Issues Enountered | None
Issued Resolved | None

## Asah (Sprint 3)
Team Member Name: | Asah Oghenerukevwe
Roles Played This Week: | Developer, Scrum Member
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Updated and finished domain model and detailed design document, helped add system to adjust for fail condition within the quiz format system, helped re-align the menu symettrically, helped craft and design visual user experience
Role duties and work to be performed next week | Act as product owner, conduct and record sprint reviews, help program flag reveal system, further update domain model and detailed design document if necessary
Issues Enountered | None
Issued Resolved | None

## Asah (Sprint 4)
Team Member Name: | Asah Oghenerukevwe
Roles Played This Week: | Product Owner, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Acted as Product Owner during Sprint Review, conducted and recorded sprint review, Created scoring system and asscoiated display, helped create the save file system
Role duties and work to be performed next week | Create expanded settings and prefrences menu, help create hang-man input system, create Architecture design patterns document update domain model and detailed design document
Issues Enountered | None
Issued Resolved | None

## Asah (Sprint 5)
Team Member Name: | Asah Oghenerukevwe
Roles Played This Week: | Developer, Scrum Member
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created expanded settings and prefrences menu, helped create hang-man input system,helped to create Architecture design patterns document, Updated Doman Model and Detailed Design document
Role duties and work to be performed next week | Help create leaderboard system, help conduct test plan, help create security documentation
Issues Enountered | None
Issued Resolved | None

## Kazi (Sprint 1)
Team Member Name: | Kazi Abdul Muktadir
Roles Played This Week: | Developer, Scrum Member
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created log for daily meetings (groupme), created Sprint Review document, created assets for use in highscore and main menu, came up with flag reveal method
Role duties and work to be performed next week | Develop new levels and encorprate more flags into game, re-adjust main menu to be more user understandable and user-friendly, add in difficulty tiers, add new info to Platform document
Issues Enountered | None
Issued Resolved | None

## Kazi (Sprint 2)
Team Member Name: | Kazi Abdul Muktadir
Roles Played This Week: | Developer, Scrum Member
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created Sprint Review 2, helped to design GRL and UCM models, helped set up and format database for flags, helped add and choose flags for database, programmed flag disply system and system to check which flags have already been guessed, as well as other parts of the random-order gamemode
Role duties and work to be performed next week | Act as Scrum Master, Create Sprint Review 3, add gamemode option for answer selection via multiple choice, help create design visuals, help create main quiz format system
Issues Enountered | None
Issued Resolved | None

## Kazi (Sprint 3)
Team Member Name: | Kazi Abdul Muktadir
Roles Played This Week: | Scrum Master, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Acted as Scrum Master for sprint reviews and meetings, created review for Sprint 3, helped add gamemode option for answer selection to be done via multiple choice, assited in the programming of the main quiz format system
Role duties and work to be performed next week | Create and reorganize gamemode selection menu so users can select their gamemode and other options, help add flag reveal system, create system for displaying hints and trivia
Issues Enountered | None
Issued Resolved | None

## Kazi (Sprint 4)
Team Member Name: | Kazi Abdul Muktadir
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created sprint review, helped update GRL and UCM models document, created interface for manging saves, helped create scoring system and implemeting it across all screens
Role duties and work to be performed next week | Create test plan documents, help create sprint reviews, help create hang-man style input method for gamemode
Issues Enountered | None
Issued Resolved | None

## Kazi (Sprint 5)
Team Member Name: | Kazi Abdul Muktadir
Roles Played This Week: | Scrum Member, Developer
Role Duties and Work Performed this week, artifacts created/updated/reviewed | Created test plan documents, helped create sprint reviews, assisted in implementing hang-man style input method for gamemode, helped add additional new flags and flag catagories to flag database
Role duties and work to be performed next week | Create test plan documents, help create sprint reviews, help create hang-man style input method for gamemode
Issues Enountered | None
Issued Resolved | None